## Slide 1: DID Mobile sprint 1
Sprint review
01.10.2015

## Slide 2: outline (do not show)
Introduction / goal
Demo
Feedback
Delivered
Not delivered
Metrics
Notes: Suggest now showing this

## Slide 3: roadmap /plan
Sprint 1
Mobile client UI
Sprint 2
Approve functionality
Sprint 3
Fine-tune the app
DID Mobile
Notes: This is the responsibility of the PO.
The arrow should point to the current sprint

## Slide 4: sprint goal
The goal of this sprint is to enable the time sheet approval via mobile.
Notes: From sprint planning notes

## Slide 5: planned deliverables
Live demo
Trial app deployed to emulator

## Slide 6: Demo

## Slide 7: planned product stories - delivered
As a Did mobile user I need to log in to the app using same web credentials
As a Did mobile user I want to see my time sheet for the current week
As a Did mobile user I should be able to see my time entries for a selected day and edit

## Slide 8: planned product stories – not delivered
As a Did mobile user I should be able to approve the current week by clicking This is what I did button

## Slide 9: other things done during the sprint
Looked into retrieve time entry data using JavaScript
Looked into web API implementation which can be used to retrieve time entry data

## Slide 10: quality
Technical debt
  Unable to access SharePoint list without SharePoint context using JavaScript

## Slide 11: quality metrics
Number of unit tests:
Unit test code coverage:

## Slide 12: sprint metrics
Planned
  10 days capacity
  62 h in tracker
  6 h/day planned velocity
Actual
  54 h logged in tracker
  18 h remaining in tracker
Actual velocity
  5.4 h/day
Notes: <hours total> in time sheet = Hours logged in calendar

## Slide 13: product owner feedback

## Slide 14: Thank you